PDSA/DMAIC WORKSHEET

Cycle:	1				    Start date for cycle: 7/1/2018		End date for cycle: 9/30/18

Project SMART aim: By 12/2019, FPQC participating hospitals will increase the percentage of LARC placement (IUD or implant) in postpartum women desiring LARC contraception from 0% to 50%.

Objective of this cycle (What are we trying to accomplish?):

Compliance with the proposed LARC implant placement process in >50% of patients who desire a LARC IUD.

LARC implant placement process compliance includes all of the following: consent obtained, order set used, provider note used, procedure note use, AND the follow-up dot phrase used

What key driver does this change impact?

Clinic, Labor and delivery, OB OR, and postpartum units are equipped to offer and perform immediate postpartum LARC insertion

PLAN OR DEFINE-MEASURE-ANALZYE

What changes can we make that will lead to improvement?

Describe changes we plan to test

- Identify appropriate candidates for IUD

- Identify patients with contraindications

- Implant and supplies for placement are readily available

- Informed consent is done appropriately

- LARC order set

- Standard documentation of LARC insertion procedure note

- Standardized method to ensure follow up instructions given to patients

Who are stakeholders for this cycle? patient, Triage and postpartum nursing staff, residents, midwives, attendings, and TGH pyxis supply people who deliver care to patients in Labor/Delivery and postpartum

Tasks needed to implement these changes (How will we make this change happen?)

| Task | Who is responsible Consider locations the changes will affect | Due date |
| --- | --- | --- |
| Add preferred contraceptive to Nurse Triage checklist | Pat | 7/15/18 |
| Informational flyer outlining appropriate candidates and contraindications | Rachel | 7/15/18 |
| Develop LARC IUD supply kits | Rachel TGH pyxis supply people | 8/1/18 |
| Develop standardized EPIC provider note for LARC placement, include confirmation of informed consent | Alyssa | 8/1/18 |
| Develop standardized EPIC procedure note | Alyssa | 8/1/18 |
| Develop LARC order set | Alyssa | 8/1/18 |
| Develop standardized EPIC dot phrase for follow-up instructions | Jessica | 8/1/18 |
| Provide project update to all stakeholders re: notes, order sets, dot phrase, supply kits, and flyer | Rachel | 8/1/18 |

Measures for this cycle (How will we know that a change is an improvement)

Consider: balancing measures, measures to determine whether the prediction succeeds and your goal is achieved, how data will be collected & who is responsible for collecting data. You may find it easier to cut and paste from your measurement grid.

| Task | Measure |
| --- | --- |
| Add preferred contraceptive to Nurse Triage checklist | % completion of checklist item on Nursing Triage checklist / # of triage patients |
| Develop standardized EPIC provider note for LARC placement, include confirmation of informed consent | % compliance with use of EPIC provider note for LARC placement/ # of implants placed |
| Develop standardized EPIC procedure note | % compliance with EPIC procedure note for LARC placement/# of implants placed |
| Develop LARC order set | % compliance with EPIC LARC order set/# of patients with LARC implant |
| Develop standardized EPIC dot phrase for follow-up instructions | Random chart review (5 charts/month) with follow up instructions in the discharge summary of patients desiring LARC implant |

Other measures

- # of LARC implants place

- qualitative feedback from 2 providers from each group – resident, attending, midwife, postpartum nurse

- LARC implant placement process compliance

DO OR IMPROVE DEFINE-MEASURE-ANALZYE

What happened when the test was conducted?

Was the cycle carried out as planned (yes, no)? No

What did you observe (i.e., qualitative feedback from the team)?

- Nurse feedback revealed that this took less time than they anticipated and were happy with the kits, once they were readily available and complete.

- Residents complained that attendings were not readily available for insertions.

- All providers were unhappy with the length of the provider note, so the note is being revised.

What did you observe that was not part of the plan?

- It took much more time to have the EMR requests fulfilled. Need to plan more time for this if further EMR requests are made.

- We needed to reset the par level for LARC implant kits in postpartum as we ran out in the 1st two weeks

- We forgot to include Kerlex in the LARC kits, so kit contents were updated.

- Providers frequently forgot the follow-up instructions dot phrase. We had to review LARC implant placements daily for 2 weeks at morning sign-out which improved compliance.

STUDY OR CONTROL

Did the measured results and observations meet your objective?

Was your goal achieved (yes, no)?  No

We achieved only 30% compliance with LARC implant placement process. The design of our cycle was ineffective because the necessary equipment was not available initially, EMR tools were available until mid-July, EMR tools were not effectively utilized by providers. We have noticed significant improvement in last 2 weeks and intend to continue our efforts.

How do results of this test compare to previous performance? NA

If YES

- Do you plan to expand the test (yes, no)?

- Will you expand the scale (i.e., keep the same conditions, just test more)?

- Will you expand the scope (i.e., change the conditions)? No

- Will you expand the scale and scope (i.e., change locations/units and conditions)? No

If NO

- What data do you have to distinguish if your method of testing the change failed or if the designed change was not effective? Design was not effective.

Were there any barriers with the cycles’ implementation (yes, no)? Yes. Delays in having equipment available and EMR tools effectively utilized.

What else did you learn?

- When EMR tools are needed for a cycle, place a ticket for these items with at least 2 month’s notice.

ACT OR CONTROL

Decide to Abandon, Adapt, or Adopt?

|  | ABANDON: Discard change idea testing. Describe what you will change. |
| --- | --- |
| x | ADAPT: Improve the change & continue a larger scale. Develop an implementation plan for sustainability. |
|  | ADOPT: Select changes to implement on & try a new one |

Continue to provide direct feedback to providers who are noncompliant with the process and further refinement of the provider documentation.