## Slide 1: Initial Verification Roadmap
Inquire
1
Start the process with FPQC the funding form with FQPC and access playbook
Prepare
Polish up policies, protocols, procedures to ensure compliance with standards
3-4 months
2
Contact TJC
3
Contact Brian Johnson to start the application process
1-2 days
TJC
4
Submit application for survey
Annual fee starts to be assessed upon application
TJC processes Application
3 days – 2 weeks/ includes phone call with Account Executive
5
Onsite
TJC surveyor(s) arrives onsite
1-2 days
6
Post Verification
7
Complete any RFIs
Celebrate!
8
Verification decision received TJC sends invoice to FPQC

## Slide 2
Tips to reduce lag time
Application submission triggers the annual fee charge
  TJC cannot bill FPQC until after the verification onsite
  Survey ready date has to be at least the day after application submission.
After submission we will work to schedule your verification close to the survey ready date
  Reduce the number of avoid dates
  Consider forgoing 30-day notice

## Slide 3
Post application email excerpts

## Slide 4
Joint Commission Cycle
E-App/
E-App updates
Onsite
Award (Day 2 - 60 after onsite)
Maintain
On average 3-4 months
2 days to 2 months
36 months post award