## Slide 1: PACC Implementation Guidance
Margie Boyer, MS, RNC-OB, EFM, ONQS
FPQC PACC Lead Nurse Consultant

## Slide 2: Keys to Building a Successful Initiative
Engage Key Stakeholders from the Start
Interdisciplinary Planning and Implementation
C- Suite Support
Consistent Commitment By All Team Members
Notes: Key Stakeholders : Bedside, front line clinicians! Family reps, Interdisciplinary work group team. C-suite champion

## Slide 3
Create a QI culture—a team environment emphasizing quality and patient safety
Hold regular QI team meetings to follow and make progress
Share important information, progress and successes with everyone impacted by PACC
Be creative and flexible!
Components of Successful Participation
Notes: Start with reviewing the WHY!
Schedule you meetings. Select a day and time
Bathroom Briefs, Gemba Board, Huddles,

## Slide 4: WHO SHOULD BE ON THE TEAM
RNs- bedside
Physicians
APRNs: CNM, CNS
Nurse Manager/Director
Quality Improvement
Informatics expert
Social Work/CM
Family Reps
Others
Notes: Interdisciplinary TEAM! The team should have a clearly identified “champion” who is committed to the project.
The optimal size of a QI team is between five and eight individuals, although this may vary. The most important requirement is not size, but diversity of the participants. It is important that the team include a diverse group of individuals who have different roles and perspectives on the project. Front line clinical team input is essential!
The IHI says that successful teams contain the following:
Clinical Leadership
Technical expertise
Day-to-day leadership
Project sponsorship

## Slide 5
Create a Culture Ready for Change
Must be an interdisciplinary effort
Teams must meet regularly
Ability to provide a safe environment for:
  Listening
  Questioning
  Persuading
  Respecting
  Helping
  Sharing
  Participating
Use the Toolkit!
Notes: Make sure you have the right people at the table. Get a commitment from all team members that they will make every effort to attend the meetings.

## Slide 6: PACC Team Meetings
  Initially meet bi-weekly or monthly depending on work
  Include all departments impacted by initiative
  Include community/family rep
  Have an agenda and share minutes.
    Review data, 30-60-90 Day Plan, PDSA cycles
    Discuss insights from webinars/coaching
  Share progress and challenges with administration – follow communication plan
    Review data, 30-60-90 Day Plan, PDSA cycles
    Discuss insights from webinars/coaching calls
Notes:   Meet bi weekly or monthly to start then may be less frequent later
  Include all departments impacted by your work
  Use agendas and take minutes items on the agenda and minutes below
  Review data, 30-60-90 Day Plan, PDSA cycles, and potential community partners
  Discuss insights from webinars/coaching
  Share progress and challenges with administration – follow communication plan

## Slide 7
Quick Start Checklist
30-60-90 Day Plan
Key Driver Diagram
PDSA Cycle

## Slide 8: Quick Start Checklist
Recruit QI team – lead, physician lead, nurse lead, QI/data lead, administrative champion
Review, complete and return PACC Data Use Agreement
Attend PACC Kick-off Meeting
Complete the PACC Pre-Implementation Survey
Write down questions or concerns
Notes: You have already done most of this you are here!

## Slide 9
Quick Start Checklist
30-60-90 Day Plan
Key Driver Diagram
PDSA Cycle
Tools to Use
Notes: Key driver models are roadmaps to particular outcomes that help focus the work . Key drivers define the pathway to a desired transformation. Key driver models graphically display the strategies and activities needed to achieve goals and aims of the practice improvement effort (DeWalt, et al., 2010).

## Slide 10
Respectful care is a universal component of every driver & activity
Comprehensive Postpartum Patient Discharge Education
Primary Key Drivers
AIM
By 6/2024, FPQC participating hospitals will:
Increase the % of patients with a 2-week PP visit scheduled prior to discharge by 20%*
Increase patient PP education~ by 20%*
Global AIM: Improve maternal health through hospital-facilitated continuum of postpartum care by coordinating and providing respectful, timely, and risk-appropriate coordinated care and services.
Clinician Postpartum Engagement and Education
Process for Maternal Discharge Risk Assessment & Arranging Early Postpartum Visits
Notes: Insert KDD here

## Slide 11
Quick Start Checklist
30-60-90 Day Plan
Key Driver Diagram
PDSA Cycle

## Slide 12: 30-60-90 Day Plan
Notes: Plan to share on coaching calls and with your individual mentor calls as well as ongoing with PACC team

## Slide 13
Notes: Start with identifying your strengths and any challenges

## Slide 14
3 Things to Accomplish in the Next 30 Days
Review interdisciplinary team members and fill any gaps
Schedule team monthly meetings for the next 6 months
Review/revise policies, procedures and education plans
Notes: Get it on the calendar!

## Slide 15
Quick Start Checklist
30-60-90 Day Plan
Key Driver Diagram
PDSA Cycle

## Slide 16: What is a PDSA cycle?
Useful tool for developing & documenting tests of change to for improvement
AKA PDCA, Deming Cycle, Shewart Cycle
P – Plan a test
D – Do a test
S – Study & learn
from test results
A – Act on results
Notes: Take 1 idea and test it out! Study, then act on outcomes. An example would be to start with 1 provider office on Post-Birth Health Check…..

## Slide 17: Reasons to test changes
Learn whether change will result in improvement
Predict the amount of improvement possible
Evaluate the proposed change work in a practice environment
Minimize resistance at implementation

## Slide 18: Potential Implementation Barriers & Strategies to Overcome
Time limitations
Strategies to Overcome
Potential Barrier Drivers
Make sure meetings are organized and succinct to decrease the impact on time
Involve bedside clinical team members-consider use of clinical ladder
Standardize meeting time for ease of scheduling; consider virtual option
Use regularly scheduled department meetings to highlight project and results-be succinct
Notes: Agendas and minutes are very important. Open clear communication with front line clinical team is essential

## Slide 19: Potential Implementation Barriers & Strategies to Overcome
Resource limitations
Connect with other hospitals or QI leaders for potential solutions; or sharing resources through collaborative work
Consider system-wide meetings to standardize best practices
Utilize your FPQC coach mentors
Strategies to Overcome
Potential Barrier Drivers
Notes: Discuss Coach Mentor Model best practices- let’s have our coach mentors present stand & introduce

## Slide 20: As the Project Continues…
Celebrate successes along the way
Display data by keeping it current AND interesting
Make it stick
  Routinization
Plan for sustainability
Notes: Celebrate successes regularly! Include all team members from bedside to executives

## Slide 21
21

## Slide 22: October-December 2022
Assess
Assess your team to assure all critical departments included
Review
Plan
Plan for PACC launch – bulletin boards; staff meetings; event invitations
Attend
Attend Data Collection Webinar:
11/10/22 Noon
Review PACC resources

## Slide 23: January 2023
Launch
Official launch at your hospital!
Plan to participate on monthly coaching calls!
Begin
Begin submitting prospective data!
Plan a call with your coach mentor!
Educate clinicians & hospital leadership on importance of PACC & facility-wide standards
Engage clinical team early & often!

## Slide 24: PACC Initiative Resources
Online Tool Box
Algorithms, Sample protocols, education tools, Slide sets, etc.
Custom, Personalized
webcam, phone, or on-site Consultations & Grand Rounds Education
Monthly and Quarterly QI Data Reports
Educational sessions, videos, and resources
Project-wide in-person collaboration meetings
Monthly e-mail Bulletins
Technical Assistance
from FPQC staff, state Clinical Advisors, and National Experts
Monthly Collaboration Calls with hospitals state-wide
Notes: Host an online PACC resource toolbox for hospital implementation
Offer guidance and feedback to participating hospitals on executing improvement strategies
Provide educational events, i.e. grand rounds and regional trainings on labor support skills
Provide email, telephone, webcam, and on-site technical assistance consultations
Convene regular learning sessions to support hospitals in driving change
Support baseline assessments and reports to assist in choosing your hospital’s improvement area
Facilitate monthly online data submission and providing monthly quality improvement data reports
Communicate progress and deliverables to the stakeholders of FPQC
Evaluate and report PROVIDE results in a fashion that does not publicly identify hospitals and providers

## Slide 25: PACC Initiative Website
http://www.fpqc.org/PACC
Click here to visit the TOOL BOX
Notes: PACC WEBSITE LINK! Host an online PACC toolbox for hospital implementation
Offer guidance and feedback to participating hospitals on executing improvement strategies
Provide educational events, i.e. grand rounds and regional trainings on labor support skills
Provide email, telephone, webcam, and on-site technical assistance consultations
Convene regular learning sessions to support hospitals in driving change
Support baseline assessments and reports to assist in choosing your hospital’s improvement area
Facilitate monthly online data submission and providing monthly quality improvement data reports
Communicate progress and deliverables to the stakeholders of FPQC
Evaluate and report PROVIDE results in a fashion that does not publicly identify hospitals and providers

## Slide 26: Questions?