# 30-60-90 Plan

## Narcan Distribution

| Foundations |  |
| --- | --- |
| Strengths | We have the support of pharmacy and administration |
| Barriers | Staff concerns about Narcan distribution |

| Looking Ahead |  |
| --- | --- |
| Things to Accomplish in the Next 30 Days | - Meet with pharmacy, ED, OB champion to learn if already participating in DCF Overdose Prevention Project (OPP); if not - Check to see if other system hospitals participating in OPP; learn if protocol can be used in this facility; if not - Review DCF OPP application form and schedule meeting with ED, pharmacy, and OB champion to discuss proposal and complete and submit OPP application |
| Things to Accomplish in Next 60 Days | 1. Work with pharmacy to extend distribution to OB floors and complete DCF harm reduction training and staff education or 2. Review protocols used in other system hospitals; meet with ED, pharmacy and OB champion to gain support; revise protocols as necessary for this facility and complete DCF OPP application form, if necessary or 3. Develop protocol for Narcan distribution in appropriate departments and update appropriate systems |
| Things to Accomplish in Next 90 Days | 1. Track Narcan distribution 2/3. Complete DCF harm reduction training and staff education and implement protocol for Narcan distribution |

Louisiana Department of Health • Office of Public Health • Bureau of Family Health